## Sheet1
PLAN
No. | Time | Work | Content
1 | Week 7 | Business Understanding | Make sure to understand what business need
2 | Week 8 | Data Understanding | Understand what kind of data we will work with
3 | Week 9 + 10 | Data Preparation | Collect data. Know how to transform data and what are extracted
4 | Week 11 | Modeling | The data model we should use
5 | Week 12 | Evaluation | The model meet the project goals
6 | Week 13 + 14 | Deployment | We use the model we developed to deploy project
7 | Week 15 | Test and finish